## Sheet1
Task | Time (estimated) | Time (spent) | Time (left) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Design & Code "Add User" interface | 1 | 1 | 0 | bar: 1
Implement "Add User" Business Logic (Code) | 2 | 2 | 0 | bar: 2 to 3
Test for "Add User" function | 1 | 1 | 0 | bar: 3
Design & Code "Edit User" interface | 1 | 1 | 0 | bar: 4
Implement "Edit User" Business Logic (Code) | 2 | 2 | 0 | bar: 4 to 5
Test for "Edit User" function | 1 | 1 | 0 | bar: 5
Design & Code "Delete User" interface | 1 | 1 | 0 | bar: 6
Implement "Delete User" Business Logic (Code) | 2 | 2 | 0 | bar: 7 to 8
Test for "Delete User" function | 1 | 1 | 0 | bar: 9
Design & Code "Add Role" interface | 1 | 1 | 0 | bar: 10
Implement "Add Role" Business Logic (Code) | 2 | 2 | 0 | 10: 2
Test for "Add Role" function | 1 | 1 | 0 | bar: 11
Design & Code "Edit Role" interface | 1 | 1 | 0 | bar: 12
Implement "Edit Role" Business Logic (Code) | 0 | 0 | 0
Test for "Edit Role" function | 0 | 0 | 0
Design & Code "Delete Role" interface | 0 | 0 | 0
Implement "Delete Role" Business Logic (Code) | 0 | 0 | 0
Test for "Delete Role" function | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Implement "Edit Role" Business Logic (Code) | 2 | 2 | 0 | 12: 2
Test for "Edit Role" function | 1 | 1 | 0 | bar: 13
Design & Code "Delete Role" interface | 1 | 1 | 0 | bar: 13
Implement "Delete Role" Business Logic (Code) | 2 | 2 | 0 | 14: 2
Test for "Delete Role" function | 1 | 1 | 0 | bar: 14
TOTAL | 24 | 24 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 0 | 2
Daily burnout | 0.2 |  |  | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7
Total time left (from estimate) |  | Estimate | 24 | 22.3 | 20.6 | 18.9 | 17.2 | 15.5 | 13.8 | 12.1 | 10.4 | 8.7 | 7 | 5.3 | 3.6 | 1.9 | 0.2
Total time left (from spent) |  | Burnout | 24 | 23 | 22 | 20 | 18 | 16 | 15 | 14 | 13 | 12 | 9 | 8 | 5 | 3 | 0
Instructions, feedback, requests and support at
http://xaviesteve.com/go/agilespreadsheet