## Sprint 3
Daily Meeting for Sprint 3 (24/02/2016 - 08/03/2016)
Member Name | What did you do yesterday? | What will you do today? | Are there any impediments in your way? | Date
Thanh |  |  |  | 24/2/2016
Nam B
Nam G
Thinh |  | Research about SQLi - Web Attacking method
Thanh |  |  |  | 25/2/2016
Nam B
Nam G |  | Add sample data for courses
Thinh
Thanh |  |  |  | 26/2/2016
Nam B
Nam G
Thinh |  | Research about SQLi - Web Attacking method
Thanh |  | Implement "Create report for CL" Business Logic (Code) |  | 27/2/2016
Nam B
Nam G |  | Fix first look UI
Thinh
Thanh |  |  |  | 28/2/2016
Nam B
Nam G | Fix first look UI | Design & Code "Create report for CL" interface
Thinh
Thanh |  | Implement "Create report for CL" Business Logic (Code) |  | 29/2/2016
Nam B
Nam G
Thinh |  | Research about SQLi - Web Attacking method
Thanh |  |  |  | 2016-01-03
Nam B
Nam G
Thinh |  | Test for "Create report - CL" function
Thanh |  | Implement "List report for CL" Business Logic (Code) |  | 2016-02-03
Nam B
Nam G |  | Design & Code "List report for CL" interface
Thinh
Thanh | Implement "List report for CL" Business Logic (Code) | Implement "List report for CL" Business Logic (Code) |  | 2016-03-03
Nam B
Nam G
Thinh |  | Test for "List report - CL" function
Thanh |  |  |  | 2016-04-03
Nam B
Nam G |  | Design & Code "Create report for CM" interface
Thinh
Thanh |  |  |  | 2016-05-03
Nam B |  | Implement "Create report for CM" Business Logic (Code)
Nam G
Thinh |  | Test for "Create report - CM" function
Thanh |  |  |  | 2016-06-03
Nam B | Implement "Create report for CM" Business Logic (Code) | Implement "Create report for CM" Business Logic (Code); Implement "List report for CM" Business Logic (Code)
Nam G
Thinh
Thanh |  |  |  | 2016-07-03
Nam B | Implement "List report for CM" Business Logic (Code) | Implement "List report for CM" Business Logic (Code)
Nam G |  | Design & Code "List report for CM" interface
Thinh
Thanh |  |  |  | 2016-08-03
Nam B
Nam G
Thinh |  | Test for "List report - CM" function