## Sheet1
Task | Time (estimated) | Time (spent) | Time (left) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Design & Code "List report for PVC" interface | 1 | 1 | 0 | bar: 1
Implement view all report as PVC | 2 | 2 | 0 | bar: 2 to 3
Test "List report for PVC" function | 1 | 1 | 0 | bar: 3
Design & Code "List report for DLT" interface | 1 | 1 | 0 | bar: 4
Implement view all report as DLT | 2 | 2 | 0 | 5: 2
Test "List report for DLT" function | 1 | 1 | 0 | bar: 6
Implement Comment in report as DLT | 2 | 2 | 0 | bar: 7 to 8
Test "Comment in report as DLT" function | 1 | 1 | 0 | bar: 9
Design & Code "View approved report for Guest" interface | 1 | 1 | 0 | bar: 10
Implement view approved report as the Guest | 0 | 0 | 0
Fix table Report | 0 | 0 | 0
Fix bug Sprint 3 | 0 | 0 | 0
Fix report status from number (1, 2, 3) to text (PENDING, APPROVED) | 0 | 0 | 0
Create Send Email Prototype | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Implement view approved report as the Guest | 2 | 2 | 0 | 11: 2
Fix table Report | 1 | 1 | 0 | bar: 12
Fix bug Sprint 3 | 3 | 3 | 0 | bar: 2; 4; 7
Fix report status from number (1, 2, 3) to text (PENDING, APPROVED) | 0.5 | 0.5 | 0 | 13: 0.5
Create Send Email Prototype | 0.5 | 0.5 | 0 | 14: 0.5
TOTAL | 19 | 19 | 0 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 2
Daily burnout | 0.8 |  |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
Total time left (from estimate) |  | Estimate | 19 | 17.7 | 16.4 | 15.1 | 13.8 | 12.5 | 11.2 | 9.9 | 8.6 | 7.3 | 6 | 4.7 | 3.4 | 2.1 | 0.8
Total time left (from spent) |  | Burnout | 19 | 18 | 16 | 14 | 12 | 10 | 9 | 7 | 6 | 5 | 4 | 2 | 1 | 0.5 | 0
Instructions, feedback, requests and support at
http://xaviesteve.com/go/agilespreadsheet