## Sheet1
Task | Time (estimated) | Time (spent) | Time (left) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Add sample data for courses | 1 | 1 | 0 | bar: 2
Research about SQLi - Web Attacking method | 4 | 4 | 0 | 1: 1; 3: 2; 6: 1
Fix first look UI | 1 | 1 | 0 | bar: 4
Design & Code "Create report for CL" interface | 1 | 1 | 0 | bar: 5
Implement "Create report for CL" Business Logic (Code) | 2 | 2 | 0 | bar: 4; 6
Test for "Create report - CL" function | 1 | 1 | 0 | bar: 7
Design & Code "List report for CL" interface | 1 | 1 | 0 | bar: 8
Implement "List report for CL" Business Logic (Code) | 2 | 2 | 0 | bar: 8 to 9
Test for "List report - CL" function | 1 | 1 | 0 | bar: 9
Design & Code "Create report for CM" interface | 1 | 1 | 0 | bar: 10
Implement "Create report for CM" Business Logic (Code) | 2 | 2 | 0 | bar: 11 to 12
Test for "Create report - CM" function | 1 | 1 | 0 | bar: 11
Design & Code "List report for CM" interface | 1 | 1 | 0 | bar: 13
Implement "List report for CM" Business Logic (Code) | 0 | 0 | 0
Test for "List report - CM" function | 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
Implement "List report for CM" Business Logic (Code) | 2 | 2 | 0 | bar: 12 to 13
Test for "List report - CM" function | 1 | 1 | 0 | bar: 14
TOTAL | 22 | 22 | 0 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2
Daily burnout | 1 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Total time left (from estimate) |  | Estimate | 22 | 20.5 | 19 | 17.5 | 16 | 14.5 | 13 | 11.5 | 10 | 8.5 | 7 | 5.5 | 4 | 2.5 | 1
Total time left (from spent) |  | Burnout | 22 | 21 | 20 | 18 | 16 | 15 | 13 | 12 | 10 | 8 | 7 | 5 | 3 | 1 | 0
Instructions, feedback, requests and support at
http://xaviesteve.com/go/agilespreadsheet