## Sprint 4
Daily Meeting for Sprint 4 (09/03/2016 - 22/03/2016)
Member Name | What did you do yesterday? | What will you do today? | Are there any impediments in your way? | Date
Thanh |  |  |  | 2016-09-03
Nam B
Nam G |  | Design & Code "List report for PVC" interface
Thinh
Thanh |  | Implement view all report as PVC; Fix bug Sprint 3 |  | 2016-10-03
Nam B |  | Fix bug Sprint 3
Nam G
Thinh
Thanh | Implement view all report as PVC | Implement view all report as PVC |  | 2016-11-03
Nam B
Nam G
Thinh |  | Test "List report for PVC" function
Thanh |  | Fix bug Sprint 3 |  | 2016-12-03
Nam B |  | Fix bug Sprint 3
Nam G |  | Design & Code "List report for DLT" interface
Thinh
Thanh |  | Implement view all report as DLT |  | 13/3/2016
Nam B
Nam G
Thinh
Thanh |  |  |  | 14/3/2016
Nam B
Nam G
Thinh |  | Test "List report for DLT" function
Thanh |  | Implement Comment in report as DLT; Fix bug Sprint 3 |  | 15/3/2016
Nam B |  | Fix bug Sprint 3
Nam G
Thinh
Thanh | Implement Comment in report as DLT | Implement Comment in report as DLT |  | 16/3/2016
Nam B
Nam G
Thinh
Thanh |  |  |  | 17/3/2016
Nam B
Nam G
Thinh |  | Test "Comment in report as DLT" function
Thanh |  |  |  | 18/3/2016
Nam B
Nam G |  | Design & Code "View approved report for Guest" interface
Thinh
Thanh |  | Implement view approved report as the Guest |  | 19/3/2016
Nam B
Nam G
Thinh
Thanh |  |  |  | 20/3/2016
Nam B |  | Fix table Report
Nam G
Thinh
Thanh |  |  |  | 21/3/2016
Nam B
Nam G
Thinh
Phuong |  | Fix report status from number (1, 2, 3) to text (PENDING, APPROVED)
Thanh |  |  |  | 22/3/2016
Nam B
Nam G
Thinh
Phuong | Fix report status from number (1, 2, 3) to text (PENDING, APPROVED) | Create Send Email Prototype