## Test case - all
Test numb | What is being tested |  | Case | Data tested | Expected results | Date | Actual results | Action taken
1 | Login function |  | Require username field | null | show message require username field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
2 |  |  | Require password field | null | show message require password field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
3 |  |  | Password field encrypt char with * | password123 | *********** | 2016-04-13 | *********** | nothing
4 |  |  | Check wrong username | username | show error message wrong username or password | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
5 |  |  | Check wrong password | password | show error message wrong username or password | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
6 |  |  | Check right user name and password | username: CL password: CL | Redirect to manager page | 2016-04-13 | Redirect to manager page | nothing
7 | Logout function |  | Click logout button | none | Redirect to login page, clear session | 2016-04-13 | Redirect to login page, session clear | nothing
8 | Role manaer function | View role group list | Load list of role group when open role manager | load from DB | List is show | 2016-04-13 | List is show | nothing
9 |  | View role group details | Click on role name to view role details | load from DB | Details is show | 2016-04-13 | Details is show | nothing
10 |  | Edit role group details | Require role name field | null | show message require role name field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
11 |  |  | Require role role field | null | show message require role field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
12 |  |  | Show message when new role group editted | role name: Test role description: This is edited description role: Admin | show message role is edited | 2016-04-13 | message is show | nothing
13 |  |  | Click edit button | role name: Test role description: This is edited description role: Admin | show message role is edited, edited details role store on DB | 2016-04-13 | message is show, data is stored | nothing
14 |  | Add new role | Require role name field | null | show message require role name field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
15 |  |  | Require role role field | null | show message require role field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
16 |  |  | Show message when new role group added | role name: Test role description: This is edited description role: Admin | show message role is added | 2016-04-13 | message is show | nothing
17 |  |  | Click save button | role name: Test role description: This is edited description role: Admin | show message role is created, edited details role store on DB | 2016-04-13 | message is show, data is stored | nothing
18 |  | Delete role | Alert when click delete role button | nothing | show confirm message | 2016-04-13 | message is show | nothing
19 |  |  | Abort delete when this role already have account | load from DB | show abort message, abort delete | 2016-04-13 | message is show, aborted delete | nothing
20 |  |  | Each role has delete button | load from DB | show delete button on each role | 2016-04-13 | new role doesn't have delete button | Request dev to fix
21 | Account manager function | View account list | Load list of account group when open account manager | load from DB | List is show | 2016-04-13 | List is show | nothing
22 |  | View account details | Click on account name to view account details | load from DB | Details is show | 2016-04-13 | Details is show | nothing
23 |  | Edit account details | Require account name field | null | show message require account name field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
24 |  |  | Require email field | null | show message require email field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
25 |  |  | Require password field | null | show message require password field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
26 |  |  | Require rle group field | null | show message require role group field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
27 |  |  | Click update role button | account name: New name email: test@gmail.com password: password123 role group: Admin | Show message updateted details, store new data on DB | 2016-04-13 | message is show, data is stored | nothing
28 |  | Add new account | Require account name field | null | show message require account name field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
29 |  |  | Require email field | null | show message require email field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
30 |  |  | Require password field | null | show message require password field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
31 |  |  | Require rle group field | null | show message require role group field | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
32 |  |  | Click save button | account name: New account email: test@gmail.com password: password123 role group: Admin | Show confirm message, store new data on DB, show messsage when new account created | 2016-04-13 | message is show, data is stored | nothing
33 |  | Delete account | Click detele button | load from DB | Show confirm message, delete account when confirm | 2016-04-13 | confirm message is show, doesn't delete data | Request dev to fix
34 | Class manager function | View class list | Load list of class when open class manager | load from DB | List is show | 2016-04-13 | List is show | nothing
35 |  | View class details | Click on details button to view class details | load from DB | Show details of selected class | 2016-04-13 | Class details is shown | nothing
36 |  | Add new class | Exists IDClass | 1 | show error message | 2016-04-13 | doesn't show error messgae, crash website | Request dev to fix
37 |  |  | Require IDClass | null | show message require IDClass | 2016-04-13 | require message is shown | nothing
38 |  |  | Require Subject | null | show message require Subject | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
39 |  |  | Require Department | null | show message require Department | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
40 |  |  | Require Title | null | show message require Title | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
41 |  |  | Click save button | IDClass: 2 Subject: Phonegap Department: Test department Title: Class title Description: none | save new class | 2016-04-13 | saved new class | nothing
42 |  | Edit class | Require Subject | null | show message require Subject | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
43 |  |  | Require Department | null | show message require Department | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
44 |  |  | Require Title | null | show message require Title | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
45 |  |  | Click save button | Subject: Phonegap edited Department: department Title: Class title Description: none | save edited information | 2016-04-13 | new information is saved | nothing
46 |  | Delete class | Click delete button | load from DB | Show confirm message, delete selected class when confirm | 2016-04-13 | confirm message is show, deleted data | nothing
47 | Students manager function | View student list | Load list of students when open students manager | load from DB | List is show | 2016-04-13 | List is show | nothing
48 |  | View student details | Click on details button to view student details | load from DB | Show details of selected student | 2016-04-13 | Student details is shown | nothing
49 |  | Add new student | Require last name field | null | show message require last name | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
50 |  |  | Require first name field | null | show message require first name | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
51 |  |  | Require address field | null | show message require address | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
52 |  |  | Require email field | null | show message require email | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
53 |  |  | Require phone field | null | show message require phone | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
54 |  |  | Click save button | Last name: Nguyen First name: Thinh Address: HTM - Ha Noi Email: thinhnguyen@gmail.com Phone: 01676666666 | save new student | 2016-04-13 | saved new student | nothing
55 |  | Edit student | Require last name field | null | show message require last name | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
56 |  |  | Require first name field | null | show message require first name | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
57 |  |  | Require address field | null | show message require address | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
58 |  |  | Require email field | null | show message require email | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
59 |  |  | Require phone field | null | show message require phone | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
60 |  |  | Click save button | Last name: Tran First name: Phuong Address: LB - Ha Noi Email: tranphuong@live.com Phone: 01676666666 | save edited information | 2016-04-13 | new information is saved | nothing
61 |  | Delete student | Click delete button | load from DB | Show confirm message, delete selected student when confirm | 2016-04-13 | confirm message is show, deleted student | nothing
62 | Course manager function | View course list | Load list of course when open course manager | load from DB | List is show | 2016-04-13 | List is show | nothing
63 |  | View course details | Click on details button to view course details | load from DB | Show details of selected course | 2016-04-13 | Course details is shown | nothing
64 |  | Add new course | Require Date | null | show message require Date | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
65 |  |  | Require Credit | null | show message require Credit | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
66 |  |  | Require Days | null | show message require Days | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
67 |  |  | Require Start time | null | show message require Start time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
68 |  |  | Require End time | null | show message require End time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
69 |  |  | Require Location | null | show message require Location | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
70 |  |  | Check end time > start time | Start time; 13-4-2016 End time: 10-4-2016 | show error message wrong time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
71 |  |  | Check start time vs end time = total day of course | Day = 30 Start time: 30-4-2016 End time: 2-5-2016 | show error message wrong time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
72 |  |  | Click save button | CMID: Admin Dates: 13-4-2016 Credits: 15 Days: 30 Stime: 15-4-2016 Etime: 15-5-2016 Location: Ha Noi FID: CL CLID: CL | Save new course | 2016-04-13 | saved new course | no thing
73 |  | Edit course | Require Date | null | show message require Date | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
74 |  |  | Require Credit | null | show message require Credit | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
75 |  |  | Require Days | null | show message require Days | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
76 |  |  | Require Start time | null | show message require Start time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
77 |  |  | Require End time | null | show message require End time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
78 |  |  | Require Location | null | show message require Location | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
79 |  |  | Check end time > start time | Start time; 13-4-2016 End time: 10-4-2016 | show error message wrong time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
80 |  |  | Check start time vs end time = total day of course | Day = 30 Start time: 30-4-2016 End time: 2-5-2016 | show error message wrong time | 2016-04-13 | doesn't show error messgae | Request dev to re-validate this field
81 |  |  | Click save button | Days: 40 | Save edited information | 2016-04-13 | saved new information | nothing
82 |  | Detele course | Click delete button | none | Show confirm message, delete selected course when confirm | 2016-04-13 | confirm message is show, deleted course | nothing
83 | CL |  | CL can view list of their report | load from DB | Show list report when CL select report menu | 2016-04-13 | List is show | nothing
84 |  |  | CL can view detail of their report | load from DB | Show details of report when click on report | 2016-04-13 | Details is shown | nothing
85 |  |  | CL can create and submit report | input | create and submmit report | 2016-04-13 | created and submmited report | nothing
86 | CM |  | CL can view list of pending report | load from DB | Show list pending report when CM select report menu | 2016-04-13 | List is show | nothing
87 |  |  | CL can view detail of their report | load from DB | Show details of report when click on report | 2016-04-13 | Details is shown | nothing
88 |  |  | CL can approve pending report | load from DB | Approve report | 2016-04-13 | Approved selected pending report | nothing
89 | DLT |  | DLT can view list of pending report | load from DB | Show list pending report when CM select report menu | 2016-04-13 | List is show | nothing
90 |  |  | DLT can view detail of their report | load from DB | Show details of report when click on report | 2016-04-13 | Details is shown | nothing
91 |  |  | DLT can approve pending report | load from DB | Approve report | 2016-04-13 | Approved selected pending report | nothing
92 | PVC |  | PVC can view list of approved report | load from DB | Show list pending report when CM select report menu | 2016-04-13 | List is show | nothing
93 |  |  | PVC can view detail of approved report | load from DB | Show details of report when click on report | 2016-04-13 | Details is shown | nothing
94 |  |  | PVC can comment on approved report | test comment | Comment to approved report | 2016-04-13 | Commented | nothing
95 |  |  | PVC can view comment on report | none | Show comment on selected report | 2016-04-13 | Comment is shown | nothing

## Spin 1
Test numb | What is being tested |  | Case | Data tested | Expected results | Date | Actual results | Action taken
1 | Role manaer function | View role group list | Load list of role group when open role manager | load from DB | List is show | 2016-02-05 | List is show | nothing
2 |  | View role group details | Click on role name to view role details | load from DB | Details is show | 2016-02-05 | Details is show | nothing
3 |  | Edit role group details | Require role name field | null | show message require role name field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
4 |  |  | Require role role field | null | show message require role field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
5 |  |  | Show message when new role group editted | role name: Test role description: This is edited description role: Admin | show message role is edited | 2016-02-05 | message is show | nothing
6 |  |  | Click edit button | role name: Test role description: This is edited description role: Admin | show message role is edited, edited details role store on DB | 2016-02-05 | message is show, data is stored | nothing
7 |  | Add new role | Require role name field | null | show message require role name field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
8 |  |  | Require role role field | null | show message require role field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
9 |  |  | Show message when new role group added | role name: Test role description: This is edited description role: Admin | show message role is added | 2016-02-05 | message is show | nothing
10 |  |  | Click save button | role name: Test role description: This is edited description role: Admin | show message role is created, edited details role store on DB | 2016-02-05 | message is show, data is stored | nothing
11 |  | Delete role | Alert when click delete role button | nothing | show confirm message | 2016-02-05 | message is show | nothing
12 |  |  | Abort delete when this role already have account | load from DB | show abort message, abort delete | 2016-02-05 | message is show, aborted delete | nothing
13 |  |  | Each role has delete button | load from DB | show delete button on each role | 2016-02-05 | new role doesn't have delete button | Request dev to fix
14 | Account manager function | View account list | Load list of account group when open account manager | load from DB | List is show | 2016-02-05 | List is show | nothing
15 |  | View account details | Click on account name to view account details | load from DB | Details is show | 2016-02-05 | Details is show | nothing
16 |  | Edit account details | Require account name field | null | show message require account name field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
17 |  |  | Require email field | null | show message require email field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
18 |  |  | Require password field | null | show message require password field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
19 |  |  | Require rle group field | null | show message require role group field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
20 |  |  | Click update role button | account name: New name email: test@gmail.com password: password123 role group: Admin | Show message updateted details, store new data on DB | 2016-02-05 | message is show, data is stored | nothing
21 |  | Add new account | Require account name field | null | show message require account name field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
22 |  |  | Require email field | null | show message require email field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
23 |  |  | Require password field | null | show message require password field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
24 |  |  | Require rle group field | null | show message require role group field | 2016-02-05 | doesn't show error messgae | Request dev to re-validate this field
25 |  |  | Click save button | account name: New account email: test@gmail.com password: password123 role group: Admin | Show confirm message, store new data on DB, show messsage when new account created | 2016-02-05 | message is show, data is stored | nothing
26 |  | Delete account | Click detele button | load from DB | Show confirm message, delete account when confirm | 2016-02-05 | confirm message is show, doesn't delete data | Request dev to fix

## Spin 2
Test numb | What is being tested |  | Case | Data tested | Expected results | Date | Actual results | Action taken
1 | Login function |  | Require username field | null | show message require username field | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
2 |  |  | Require password field | null | show message require password field | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
3 |  |  | Password field encrypt char with * | password123 | *********** | 2016-02-15 | *********** | nothing
4 |  |  | Check wrong username | username | show error message wrong username or password | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
5 |  |  | Check wrong password | password | show error message wrong username or password | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
6 |  |  | Check right user name and password | username: CL password: CL | Redirect to manager page | 2016-02-15 | Redirect to manager page | nothing
7 | Logout function |  | Click logout button | none | Redirect to login page, clear session | 2016-02-15 | Redirect to login page, session clear | nothing
8 | Course manager function | View course list | Load list of course when open course manager | load from DB | List is show | 2016-02-15 | List is show | nothing
9 |  | View course details | Click on details button to view course details | load from DB | Show details of selected course | 2016-02-15 | Course details is shown | nothing
10 |  | Add new course | Require Date | null | show message require Date | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
11 |  |  | Require Credit | null | show message require Credit | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
12 |  |  | Require Days | null | show message require Days | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
13 |  |  | Require Start time | null | show message require Start time | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
14 |  |  | Require End time | null | show message require End time | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
15 |  |  | Require Location | null | show message require Location | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
16 |  |  | Check end time > start time | Start time; 13-4-2016 End time: 10-4-2016 | show error message wrong time | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
17 |  |  | Check start time vs end time = total day of course | Day = 30 Start time: 30-4-2016 End time: 2-5-2016 | show error message wrong time | 2016-02-15 | doesn't show error messgae | Request dev to re-validate this field
18 |  |  | Click save button | CMID: Admin Dates: 13-4-2016 Credits: 15 Days: 30 Stime: 15-4-2016 Etime: 15-5-2016 Location: Ha Noi FID: CL CLID: CL | Save new course | 2016-02-15 | saved new course | no thing
19 |  | Edit course | Require Date | null | show message require Date | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
20 |  |  | Require Credit | null | show message require Credit | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
21 |  |  | Require Days | null | show message require Days | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
22 |  |  | Require Start time | null | show message require Start time | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
23 |  |  | Require End time | null | show message require End time | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
24 |  |  | Require Location | null | show message require Location | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
25 |  |  | Check end time > start time | Start time; 13-4-2016 End time: 10-4-2016 | show error message wrong time | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
26 |  |  | Check start time vs end time = total day of course | Day = 30 Start time: 30-4-2016 End time: 2-5-2016 | show error message wrong time | 2016-02-20 | doesn't show error messgae | Request dev to re-validate this field
27 |  |  | Click save button | Days: 40 | Save edited information | 2016-02-20 | saved new information | nothing
28 |  | Detele course | Click delete button | none | Show confirm message, delete selected course when confirm | 2016-02-20 | confirm message is show, deleted course | nothing

## Spin 3
Test numb | What is being tested |  | Case | Data tested | Expected results | Date | Actual results | Action taken
1 | CL |  | CL can view list of their report | load from DB | Show list report when CL select report menu | 2016-03-03 | List is show | nothing
2 |  |  | CL can view detail of their report | load from DB | Show details of report when click on report | 2016-03-03 | Details is shown | nothing
3 |  |  | CL can create and submit report | input | create and submmit report | 2016-03-03 | created and submmited report | nothing
4 | CM |  | CL can view list of pending report | load from DB | Show list pending report when CM select report menu | 2016-03-03 | List is show | nothing
5 |  |  | CL can view detail of their report | load from DB | Show details of report when click on report | 2016-03-03 | Details is shown | nothing
6 |  |  | CL can approve pending report | load from DB | Approve report | 2016-03-03 | Approved selected pending report | nothing
7 | Class manager function | View class list | Load list of class when open class manager | load from DB | List is show | 2016-03-10 | List is show | nothing
8 |  | View class details | Click on details button to view class details | load from DB | Show details of selected class | 2016-03-10 | Class details is shown | nothing
9 |  | Add new class | Exists IDClass | 1 | show error message | 2016-03-10 | doesn't show error messgae, crash website | Request dev to fix
10 |  |  | Require IDClass | null | show message require IDClass | 2016-03-10 | require message is shown | nothing
11 |  |  | Require Subject | null | show message require Subject | 2016-03-10 | doesn't show error messgae | Request dev to re-validate this field
12 |  |  | Require Department | null | show message require Department | 2016-03-10 | doesn't show error messgae | Request dev to re-validate this field
13 |  |  | Require Title | null | show message require Title | 2016-03-10 | doesn't show error messgae | Request dev to re-validate this field
14 |  |  | Click save button | IDClass: 2 Subject: Phonegap Department: Test department Title: Class title Description: none | save new class | 2016-03-10 | saved new class | nothing
15 |  | Edit class | Require Subject | null | show message require Subject | 2016-03-10 | doesn't show error messgae | Request dev to re-validate this field
16 |  |  | Require Department | null | show message require Department | 2016-03-10 | doesn't show error messgae | Request dev to re-validate this field
17 |  |  | Require Title | null | show message require Title | 2016-03-10 | doesn't show error messgae | Request dev to re-validate this field
18 |  |  | Click save button | Subject: Phonegap edited Department: department Title: Class title Description: none | save edited information | 2016-03-10 | new information is saved | nothing
19 |  | Delete class | Click delete button | load from DB | Show confirm message, delete selected class when confirm | 2016-03-10 | confirm message is show, deleted data | nothing

## Spin 4
Test numb | What is being tested |  | Case | Data tested | Expected results | Date | Actual results | Action taken
1 | DLT |  | DLT can view list of pending report | load from DB | Show list pending report when CM select report menu | 2016-03-15 | List is show | nothing
2 |  |  | DLT can view detail of their report | load from DB | Show details of report when click on report | 2016-03-15 | Details is shown | nothing
3 |  |  | DLT can approve pending report | load from DB | Approve report | 2016-03-15 | Approved selected pending report | nothing
4 | PVC |  | PVC can view list of approved report | load from DB | Show list pending report when CM select report menu | 2016-03-15 | List is show | nothing
5 |  |  | PVC can view detail of approved report | load from DB | Show details of report when click on report | 2016-03-15 | Details is shown | nothing
6 |  |  | PVC can comment on approved report | test comment | Comment to approved report | 2016-03-15 | Commented | nothing
7 |  |  | PVC can view comment on report | none | Show comment on selected report | 2016-03-15 | Comment is shown | nothing
8 | Students manager function | View student list | Load list of students when open students manager | load from DB | List is show | 2016-03-15 | List is show | nothing
9 |  | View student details | Click on details button to view student details | load from DB | Show details of selected student | 2016-03-15 | Student details is shown | nothing
10 |  | Add new student | Require last name field | null | show message require last name | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
11 |  |  | Require first name field | null | show message require first name | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
12 |  |  | Require address field | null | show message require address | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
13 |  |  | Require email field | null | show message require email | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
14 |  |  | Require phone field | null | show message require phone | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
15 |  |  | Click save button | Last name: Nguyen First name: Thinh Address: HTM - Ha Noi Email: thinhnguyen@gmail.com Phone: 01676666666 | save new student | 2016-03-15 | saved new student | nothing
16 |  | Edit student | Require last name field | null | show message require last name | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
17 |  |  | Require first name field | null | show message require first name | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
18 |  |  | Require address field | null | show message require address | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
19 |  |  | Require email field | null | show message require email | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
20 |  |  | Require phone field | null | show message require phone | 2016-03-15 | doesn't show error messgae | Request dev to re-validate this field
21 |  |  | Click save button | Last name: Tran First name: Phuong Address: LB - Ha Noi Email: tranphuong@live.com Phone: 01676666666 | save edited information | 2016-03-15 | new information is saved | nothing
22 |  | Delete student | Click delete button | load from DB | Show confirm message, delete selected student when confirm | 2016-03-15 | confirm message is show, deleted student | nothing