## Sheet1
Daily Meeting for Sprint 1 (27/01/2016 - 17/02/2016)
Member Name | What did you do yesterday? | What will you do today? | Are there any impediments in your way? | Date
Thinh | NA | Gather highest priority functions the will be implemented in sprint 1 | NA | 2016-01-26
Phuong | NA | Gather highest priority functions the will be implemented in sprint 1 | NA
Tung |  | Gather requirement
Thanh |  | Research for database
Nam G |  | Update source code to github
Nam B |  | Create document
Sprint backlog - Sprint 1
Thinh | research for system functions | Implement authentication and authorization |  | 2016-01-27
Phuong | research for system functions | Implement authentication and authorization
Tung | Productbacklog | Scrum practices
Thanh | Database design | Database design
NamG | Database design | research for interface
NamB | Database design | research for database (integrity)
Thinh | Authentication and authorization | Test login, logout |  | 2016-02-02
Phuong | Authentication and authorization | Test permission
Tung | Study about Scrum | Test plan
Thanh | Database design | Test database
NamG | UI and web interface | Design interface
NamB | Database design | Test database
Thinh | Test accsess | research about web security |  | 2016-02-16
Phuong | Test accsess | research about web security
Tung | Scrum practices | Test plan
Thanh | database test | research for database (normalization)
Nam G | interface desgin | reseach for Responsive web design
Nam B | test database | research for database (normalization)